## ProjectBreakdown
|  | Project Data | [9 empty] | Project Phases | [6 empty] | Milestones
Main Label | Second Label | Task Label | SLyL | MLyL | SLxL | Task Start | Task Duraction in Quarters |  | TDName | TyL |  | Name | Phase Start in Quarters | Phase Duraction in Quarters | Pmiddle | Pend | Pheight |  | Label | Second Label | Mile Start | Mheight
2021 | Q1 | Game Design | 0 | -20 | 1 | 1 | 1 | 2 | 12 Week(s) | 120 |  | Pre-Production | 1 | 2 | 2 | 3 | -30 | 10 | Pre-Alpha | (End of September 21) | 3 | 18
| Q2 | Low level planning | 0 | -20 | 2 | 2.5 | 1 | 3.5 | 12 Week(s) | 110 |  | Development | 3 | 6 | 6 | 9 | -40 |  | Alpha | (End of March 22) | 5 | 18
| Q3 | Prototyping | 0 | -20 | 3 | 3 | 2 | 5 | 24 Week(s) | 100 |  | Polish | 9 | 3 | 10.5 | 12 | -30 |  | Beta | (End of March 23) | 9 | 18
| Q4 | Game Logic | 0 | -20 | 4 | 4 | 5 | 9 | 60 Week(s) | 90 |  | Maintenance | 12 | 2 | 13 | 14 | -40 |  | Gold-Master | (End of September 23) | 11 | 30
2022 | Q1 | Asset Creation | 0 | -20 | 5 | 4 | 5 | 9 | 60 Week(s) | 80 | [8 empty] | Release | (End of December 23) | 12 | 18
| Q2 | Alpha Testing | 0 | -20 | 6 | 5 | 0.34 | 5.34 | 4 Week(s) | 70
| Q3 | Beta Testing | 0 | -20 | 7 | 8 | 0.34 | 8.34 | 4 Week(s) | 60
| Q4 | Bug Fixing | 0 | -20 | 8 | 9 | 2 | 11 | 24 Week(s) | 50
2023 | Q1 | Release Preperations | 0 | -20 | 9 | 10 | 2 | 12 | 24 Week(s) | 40 | 10
| Q2 | Maintenance/Support | 0 | -20 | 10 | 12 | 2 | 14 | 24 Week(s) | 30
| Q3 |  | 0 | -20 | 11
| Q4 |  | 0 | -20 | 12
2024 | Q1 |  | 0 | -20 | 13

## ProjectTimeline
Timeline |  |  |  | Goals
MLyL | SLyL | Goal Description | Gy | Gdy
-2 | -1 | We have focused on gathering information about the end user, highlighted the business contraints and found the fun of the project. This will be the colmination of the pre-production phase. | 8 | 7 | 0 | 6
-2 | -1 | We have finished prototyping solutions that meet the needs of the end-user. We have "hopefully" discovered all problems with our design and established technical feasibility. All documentation is finished and we are ready to start development. | -4 | -5 | 0 | -4
-2 | -1 | A working version of the product, based on what was learning in the alpha prototypes. We have intergrated the product into existing services, and are preparing for a transition to go live and release. | 8 | 7 | 0 | 6
-2 | -1 | A release version of the product, we could release now if we wanted. However, small bugs and issues may still be in the product, nothing to serious, nevertheless still things that need to be solved. | -4 | -5 | 0 | -4
-2 | -1 | The final version of the product, we will continue monitoring user experiences and make adjustments here and there where needed. | 8 | 7 | 0 | 6
-2 | -1
-2 | -1
-2 | -1
-2 | -1
-2 | -1
-2 | -1
-2 | -1
-2 | -1