## Project Info
Chart Info:
Priority vs Ranking | The difference between Priority and Ranking is that Ranking defined value towards product, while Priority defines in which order the features will be made.
Project Info: |  | Developers: |  |  |  | Milestones:
Start Date: | 2022-06-28 | Name | Disipline | Days a week | Total Available | Name | Date | Days | Weeks
End Date: | 2023-07-01 | Programmer 1 | Code | 5 | 160 | Kickoff |  | 5 | 1
Total Dev Days: | 264 | Programmer 2 | Code | 3 | 96 | Milestone 1 | 2022-07-01 | 4 | 0.8
70% Budget Rule: | 184.8 | Designer 1 | Design | 4 | 128 | Milestone 2 | 2022-08-01 | 22 | 4.4
|  | Producer 1 | Production | 3 | 96
|  | Artist 1 | Art | 4.5 | 144
Formulas:
Days = NETWORKDAYS(C6, [Date])
Days = NETWORKDAYS([Date, row above], [Date])

## Features
[8 empty] | In Days | 100% Effect Division
[8 empty] | Costs 70% of Budget | Prod | Tech | Art | Audio | UI/UX | Design
[9 empty] | Production | Code | Art | Sound | Design | Design
|  | Order of Feature |  | Importance of Feature | Departments Envolved |  |  | Total % | 28 | 18 | 36 | 2 | 0 | 16
State | Milestone | Priority | Complexity (1 to 5) | Ranking (MoSCoW) | What is needed? | Feature Name | Explained Feature | Total: 50 of Days | 14 | 9 | 18 | 1 | 0 | 8 | Notes
In Progress | Kickoff | Normal | 2 | Must | Presentation | Kick off presentation | For the project we need a kick off presentation that will explain the scope, feature list and timeline | 10 | 6 | 1 | 1 | 1 | 0 | 1
Not Started | Milestone 1 | High | 3 | Must | Document | Art style document | For the project we need a document that conveys the art style of the project | 15 | 3 | 3 | 7 | 0 | 0 | 2
Not Started | Milestone 2 | Normal | 5 | Should | Art Assets | Number of art assets | For the project we need large number of random art assets | 25 | 5 | 5 | 10 | 0 | 0 | 5

## Milestones and developers
Days per Milestone:
|  | Kickoff | Milestone 1 | Milestone 2 | 0 | 0 | 0 | 0 | 0
Days for Mil: |  | 5 | 4 | 22 | 0 | 0 | 0 | 0 | 0
Days for Dev: |  | 10 | 15 | 25 | 0 | 0 | 0 | 0 | 0
Difference: |  | -5 | -11 | -3 | 0 | 0 | 0 | 0 | 0
Disiplines needed per milestone:
|  | Kickoff | Milestone 1 | Milestone 2 | 0 | 0 | 0 | 0 | 0
Code |  | 1 | 3 | 5 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Art |  | 1 | 7 | 10 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Design |  | 1 | 2 | 5 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Sound |  | 1 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Production |  | 6 | 3 | 5 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | 10 | 15 | 25 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Disiplines scheduled per milestone:
|  | Kickoff | Milestone 1 | Milestone 2 | 0 | 0 | 0 | 0 | 0
Code | 40.6 | 7 | 3.4 | 30.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Art | 9.9 | 3.5 | -3.4 | 9.8 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Design | 16.8 | 3 | 1.2 | 12.6 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Sound | -1 | -1 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Production | 4.6 | -3 | -0.6 | 8.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## Lists (hidden)
Not Started | Very High | Must | Code
In Progress | High | Should | Art
Depricated | Normal | Could | Design
Reviewed | Low | Would | Sound
On Hold | Very Low |  | Production
Completed